## Summary
|  | Project: | Office/Warehouse
|  | Address: | 1234 Campus Drive, Orem
|  | Bldg SF: | 25000
|  | Estimator: | Rob Warcup
Self-Performed Work |  | Labor | Material | Equip | Subs | Other | Estimate | $/SF | Actual | Variance
| Excavation & Backfill | 8770 | 14579 | 8478 |  |  | 31827 | 1.2731 | 32550 | -723
| Formwork | 29707 | 8184 |  |  |  | 37891 | 1.5156 | 35620 | 2271
| Concrete Work | 8663 | 70387 | 4148 |  |  | 83198 | 3.3279 | 82114 | 1084
| Misc. Concrete Work | 31525 | 19780 | 1457 | 10278 |  | 63040 | 2.5216 | 66954 | -3914
| Masonry Work | 33364 | 48306 | 980 |  |  | 82650 | 3.306 | 91256 | -8606
| Subtotal | 112029 | 161236 | 15063 | 10278 | 0 | 298606 | 11.9442 | 308494 | -9888
| Running Total | 112029 | 161236 | 15063 | 10278 | 0 | 298606 | 11.9442 | 308494 | -9888
Subcontractors |  | Labor | Material | Equip | Subs | Other | Estimate | $/SF | Actual | Variance
| Finish Hardware Allowance |  |  |  | 7000 |  | 7000 | 0.28 | 7000 | 0
| Site Paving |  |  |  | 40460 |  | 40460 | 1.6184 | 41253 | -793
| Landscaping |  |  |  | 10027 |  | 10027 | 0.40108 | 9599 | 428
| Piling |  |  |  | 31500 |  | 31500 | 1.26 | 31500 | 0
| Reinforcing Steel |  |  |  | 54025 |  | 54025 | 2.161 | 54025 | 0
| Steel Building |  |  |  | 555000 |  | 555000 | 22.2 | 542087 | 12913
| Misc. Steel | 2783 |  |  | 9275 |  | 12058 | 0.48232 | 15684 | -3626
| Carpentry |  |  |  | 24297.5683 |  | 24297.5683 | 0.9719 | 9000 | 15297.5683
| Millwork & Wood Doors | 5550 |  |  | 18500 |  | 24050 | 0.962 | 24050 | 0
| Roofing |  |  |  | 76000 |  | 76000 | 3.04 | 76000 | 0
| Caulking & Damp-proofing |  |  |  | 2250 |  | 2250 | 0.09 | 2250 | 0
| Hollow Metal Doors & Frames | 1040 |  |  | 10200 |  | 11240 | 0.4496 | 11240 | 0
| Overhead Doors |  |  |  | 36000 |  | 36000 | 1.44 | 36000 | 0
| Windows |  |  |  | 62406 |  | 62406 | 2.4962 | 64852 | -2446
| Resilient Floors |  |  |  | 50205 |  | 50205 | 2.0082 | 51625 | -1420
| Drywall |  |  |  | 38492 |  | 38492 | 1.5397 | 36551 | 1941
| Acoustic Ceiling |  |  |  | 15305 |  | 15305 | 0.6122 | 15200 | 105
| Painting |  |  |  | 24240 |  | 24240 | 0.9696 | 24240 | 0
| Toilet Partitions |  |  |  | 6480 |  | 6480 | 0.2592 | 6480 | 0
| Washroom Accessories | 800 |  |  | 1625 |  | 2425 | 0.097 | 2425 | 0
| Plumbing & HVAC |  |  |  | 206250 |  | 206250 | 8.25 | 198557 | 7693
| Electrical |  |  |  | 142550 |  | 142550 | 5.702 | 146394 | -3844
| Subtotal | 10173 | 0 | 0 | 1422087.5683 | 0 | 1432260.5683 | 57.2904 | 1406012 | 26248.5683
| Running Total | 122202 | 161236 | 15063 | 1432365.5683 | 0 | 1730866.5683 | 69.2347 | 1714506 | 16360.5683
General Expenses |  | Labor | Material | Equip | Subs | Other | Estimate | $/SF | Actual | Variance
| General Expenses Subtotal | 93825 | 8640 | 20514 | 7700 | 30510 | 161189 | 6.4476 | 184562 | -23373
| Running Total | 216027 | 169876 | 35577 | 1440065.5683 | 30510 | 1892055.5683 | 75.6822 | 1899068 | -7012.4317
Add-Ons |  | Labor | Material | Equip | Subs | Other | Estimate | $/SF | Actual | Variance
3% | Small Tools (% of Labor) |  |  |  |  | 6480.81 | 6480.81 | 0.25923 | 5421 | 1059.81
25% | Payroll Additive (% of Labor) |  |  |  |  | 54006.75 | 54006.75 | 2.1603 | 54000 | 6.75
12% | State Taxes (% of Mat'l) |  |  |  |  | 20385.12 | 20385.12 | 0.8154 | 19985 | 400.12
| Building Permit ($6 for every $1000 of Bid) |  |  |  |  | 12600 | 12600 | 0.504 | 12137 | 463 | 12654.3195
| 50% Bond ($7.25 for every $1000 of Bid) |  |  |  |  | 15225 | 15225 | 0.609 | 15225 | 0 | 15290.636
| Insurance ($3 for every $1000 of Bid) |  |  |  |  | 6300 | 6300 | 0.252 | 6120 | 180 | 6327.1597
| Fee |  |  |  |  | 102000 | 102000 | 4.08 | 81700 | 20300 | 4.836%
| Subtotal | 0 | 0 | 0 | 0 | 216997.68 | 216997.68 | 8.6799 | 194588 | 22409.68
| Bid Total/Running Total | 216027 | 169876 | 35577 | 1440065.5683 | 247507.68 | 2109053.2483 | 84.3621 | 2093656 | 15397.2483

## Carpentry
PT bottom plate
Double top plate
116-5/8" studs
Headers: 3-1/2x9-1/2" LVL over all doorways (no windows)
3/4" OSB Sheathing on roof and under siding
PT plate on top of CMU wall
Material | [11 empty] | Labor | [5 empty] | 1/12 slope on roof sheathing
Pressure Treated Material 2x4 & 2x6 | [5 empty] | Net LF*W/St L | [5 empty] | Pressure Treated Material 2x4 & 2x6
| Area Description | Mat'l Description | Net (LF) | Waste | Stick Lngth' | #Pcs | $/Stick | Ext. Total |  |  |  |  | BF/Pc | BF Total | Operation | Prod. UOM | Low | High | Select Prod. | Ext. Hrs.
| 2x4 Bottom Plate | 2x4x16 Pressure Treated | 413 | 1.1 | 16 | 29 | 5.789 | 167.881 |  |  |  |  | 10.6667 | 309.3333 | 2x4 Plates | BF/Hr | 63 | 68 | 68 | 4.549
| 2x6 Bottom Plate | 2x6x16 Pressure Treated | 22 | 1.1 | 16 | 2 | 8.351 | 16.702 |  |  |  |  | 16 | 32 | 2x6 Plates | BF/Hr | 90 | 95 | 95 | 0.33684
| 2x4 Garage Bottom Plate | 2x4x16 Pressure Treated | 87 | 1.1 | 16 | 6 | 5.789 | 34.734 |  |  |  |  | 10.6667 | 64 | 2x4 Plates | BF/Hr | 63 | 68 | 68 | 0.94118
|  |  | 522 |  |  | 37 |  | 219.317 | [11 empty] | 5.827
Plate Material 2x4 & 2x6 | [6 empty] | Net LF*W/St L*# Pl |  |  |  |  | Plate Material 2x4 & 2x6
| Area Description | Mat'l Description | Net (LF) | Waste | Stick Length' | # Plates | # Pcs | $/Stick | Ext. Total |  |  |  | BF/Pc | BF Total | Operation | Prod. UOM | Low | High | Select Prod. | Ext. Hrs.
| 2x4 Basement Dbl Top | 2x4x16 | 208 | 1.1 | 16 | 2 | 29 | 5.85 | 169.65 |  |  |  | 10.6667 | 309.3333 | 2x4 Plates | BF/Hr | 63 | 68 | 68 | 4.549
| 2x6 Basement Dbl Top | 2x6x16 | 16 | 1.1 | 16 | 2 | 3 | 9.14 | 27.42 |  |  |  | 16 | 48 | 2x6 Plates | BF/Hr | 90 | 95 | 95 | 0.50526
| 2x6 Main Floor Ext. | 2x6x16 | 194 | 1.1 | 16 | 3 | 41 | 9.14 | 374.74 |  |  |  | 16 | 656 | 2x4 Plates | BF/Hr | 63 | 68 | 68 | 9.6471
| 2x4 Main Floor Int. | 2x4x16 | 385 | 1.1 | 16 | 3 | 80 | 5.85 | 468 |  |  |  | 10.6667 | 853.3333 | 2x4 Plates | BF/Hr | 63 | 68 | 68 | 12.549
| 2x4 Garage | 2x4x16 | 87 | 1.05 | 16 | 2 | 12 | 5.85 | 70.2 |  |  |  | 10.6667 | 128 | 2x4 Plates | BF/Hr | 63 | 68 | 68 | 1.8824
| Bracing | 2x4x12 | 300 | 1 | 12 | 1 | 25 | 4.19 | 104.75 |  |  |  | 8 | 200 | 2x4 Plates | BF/Hr | 63 | 68 | 68 | 2.9412
|  |  | 1190 |  |  |  | 190 |  | 1214.76 | [10 empty] | 32.0739
Studs | [5 empty] | LF Wall*Mult | [5 empty] | Studs
| Area Description | Stud Size | LF Wall | OC Spacing | Multiplier | # Pcs | $/Stud | Ext. Total |  |  |  |  | BF/Pc | BF Total | Operation | Prod. UOM | Low | High | Select Prod. | Ext. Hrs.
| 2x6 Ext Walls | 2x6x104-5/8 | 220 | 16" OC | 1 | 220 | 4.88 | 1073.6 |  |  |  |  | 9 | 1980 | 2x6 Studs | BF/Hr | 110 | 125 | 125 | 15.84
| 2x4 Int Walls | 2x4x92-5/8 | 185 | 24" OC | 0.75 | 139 | 2.43 | 337.77 |  |  |  |  | 5.3333 | 741.3333 | 2x4 Studs | BF/Hr | 100 | 115 | 115 | 6.4464
| 2x6 Bath | 2x6x92-5/8 | 35 | 24" OC | 0.75 | 27 | 4.42 | 119.34 |  |  |  |  | 8 | 216 | 2x6 Studs | BF/Hr | 110 | 125 | 125 | 1.728
| 2x4 Garage Walls | 2x4x116-5/8 | 55 | 16" OC | 1 | 55 | 3.64 | 200.2 |  |  |  |  | 6.6667 | 366.6667 | 2x4 Studs | BF/Hr | 100 | 115 | 115 | 3.1884
| 2x6 Main Floor Ext Walls | 2x6x104-5/8 | 202 | 16" OC | 1 | 202 | 4.88 | 985.76 |  |  |  |  | 9 | 1818 | 2x6 Studs | BF/Hr | 110 | 125 | 125 | 14.544
| 2x4 Main Floor Int Walls | 2x4x104-5/8 | 196 | 24" OC | 0.75 | 147 | 2.9 | 426.3 |  |  |  |  | 6 | 882 | 2x4 Studs | BF/Hr | 100 | 115 | 115 | 7.6696
|  |  | 893 |  |  | 790 |  | 3142.97 | [11 empty] | 49.4163
Joists |  |  |  |  | Length*# Joists | [6 empty] | Joists
| Area Description | Mat'l Descr. | Length' | #joists | LF | $/LF | Ext. Total | [5 empty] | LF/1' | LF Total | Operation | Prod. UOM | Low | High | Select Prod. | Ext. Hrs.
| Exam 1 & reception | 2-1/2" x 16" I-Joist | 25 | 8 | 200 | 4.16 | 832 | [5 empty] | 1 | 200 | 16" Joists/Rim | LF/Hr | 250 | 270 | 270 | 0.74074
| Waiting | 2-1/2" x 16" I-Joist | 16 | 4 | 64 | 4.16 | 266.24 | [5 empty] | 1 | 64 | 16" Joists/Rim | LF/Hr | 250 | 270 | 270 | 0.23704
| Waiting & Restrooms | 2-1/2" x 16" I-Joist | 23 | 3 | 69 | 4.16 | 287.04 | [5 empty] | 1 | 69 | 16" Joists/Rim | LF/Hr | 250 | 270 | 270 | 0.25556
| Exam 2 & 3 | 3-1/2" x 16" I-Joist | 28 | 7 | 196 | 4.65 | 911.4 | [5 empty] | 1 | 196 | 16" Joists/Rim | LF/Hr | 250 | 270 | 270 | 0.72593
|  |  | 92 |  | 529 |  | 2296.68 | [12 empty] | 1.9593
Wall & Floor Sheathing | [5 empty] | SF/P-SF*W | [5 empty] | Wall & Floor Sheathing
| Area Description | Mat'l Description | SF | Panel SF | Waste | # Panels | $/Panel | Ext. Total |  |  |  |  | SF/Pc | SF Total | Operation | Prod. UOM | Low | High | Select Prod. | Ext. Hrs.
| Front Elev | 4x10 x 3/8" OSB | 782 | 40 | 1.05 | 21 | 6.08 | 127.68 |  |  |  |  | 40 | 840 | Wall Sheathing | SF/Hr | 130 | 150 | 150 | 5.6
| Rt Elev | 4x10 x 3/8" OSB | 645 | 40 | 1.05 | 17 | 6.08 | 103.36 |  |  |  |  | 40 | 680 | Wall Sheathing | SF/Hr | 130 | 150 | 150 | 4.5333
| Lt Elev | 4x10 x 3/8" OSB | 645 | 40 | 1.05 | 17 | 6.08 | 103.36 |  |  |  |  | 40 | 680 | Wall Sheathing | SF/Hr | 130 | 150 | 150 | 4.5333
| Rear Elev | 4x10 x 3/8" OSB | 690 | 40 | 1.05 | 19 | 6.08 | 115.52 |  |  |  |  | 40 | 760 | Wall Sheathing | SF/Hr | 130 | 150 | 150 | 5.0667
| 2nd floor | 4x8 x 3/4" OSB T&G | 1966 | 32 | 1.1 | 68 | 9.982 | 678.776 |  |  |  |  | 32 | 2176 | T&G Floors | SF/Hr | 150 | 160 | 160 | 13.6
|  |  | 4728 |  |  | 142 |  | 1128.696 | [11 empty] | 33.3333
Roof Sheathing | [5 empty] | SF(2D)/P-SF*W |  |  | #P(2D)*M |  |  | Roof Sheathing
| Area Description | Mat'l Description | SF (2D) | Panel SF | Waste | # Panels (2D) | Slope/12 | Mult. | # Panels | $/Panel | Ext. Total |  | SF/Pc | SF Total | Operation | Prod. UOM | Low | High | Select Prod. | Ext. Hrs.
| Common Truss/Main Roof | 4x8 x 1/2" OSB | 4258 | 32 | 1.15 | 153.0219 | 8 | 1.2019 | 184 | 5.712 | 1051.008 |  | 32 | 5888 | Roof Sheathing | SF/Hr | 160 | 180 | 180 | 32.7111
| Front Garage Gable | 4x8 x 1/2" OSB | 364 | 32 | 1.15 | 13.0812 | 10 | 1.3017 | 18 | 5.712 | 102.816 |  | 32 | 576 | Roof Sheathing | SF/Hr | 160 | 180 | 180 | 3.2
| Outbuilding | 4x8 x 1/2" OSB | 225 | 32 | 1.15 | 8.0859 | 10 | 1.3017 | 11 | 5.712 | 62.832 |  | 32 | 352 | Roof Sheathing | SF/Hr | 160 | 180 | 180 | 1.9556
|  |  | 4847 |  |  | 174.1891 |  |  | 213 |  | 1216.656 | [8 empty] | 37.8667
Rimboard | [5 empty] | LF/Rim L'*W | [5 empty] | Rimboard
| Area Description | Mat'l Description | LF of Rim | Rim Length' | Waste | # Pcs | $/Stick | Ext. Total |  |  |  |  | LF/Pc | LF Total | Operation | Prod. UOM | Low | High | Select Prod. | Ext. Hrs.
| 2nd Floor Rim | 1-1/8" x 16" x 20' Rim | 315 | 20 | 1.05 | 17 | 37.01 | 629.17 |  |  |  |  | 20 | 340 | 16" Joists/Rim | LF/Hr | 250 | 270 | 270 | 1.2593
| 1st Floor Rim | 1-1/8" x 16" x 20' Rim | 422 | 20 | 1.05 | 23 | 37.01 | 851.23 |  |  |  |  | 20 | 460 | 16" Joists/Rim | LF/Hr | 250 | 270 | 270 | 1.7037
|  |  | 737 |  |  | 40 |  | 1480.4 | [11 empty] | 2.963
Header Material | [11 empty] | Header Material
| Area Description | Mat'l Description | ? | ? | ? | LF | [6 empty] | BF/Pc | BF Total | Operation | Prod. UOM | Low | High | Select Prod. | Ext. Hrs.
Trusses | [11 empty] | Trusses
| Description | UOM | $/Unit | Qty | Ext. Total | [7 empty] | X | No. Total | Operation | Prod. UOM | Low | High | Select Prod. | Ext. Hrs.
| Truss Package | LS | 1350 | 1 | 1350 | [8 empty] | 33 | Trusses 24'-40' Span | No./Hr | 2 | 3 | 10 | 3.3
[5 empty] | 1350 | [14 empty] | 3.3
Equipment | [11 empty] | Labor Costs |  |  |  | Auto-populated Labor Hrs from Estimate Summary
| Description | UOM | $/Unit | # Hrs,Days | Ext. Total | [7 empty] | Crew Member | Allocation | $/Hr | Total Hrs | Ext. Total
| Crane Rental | Hrs | 200 | 3.3 | 660 | [7 empty] | Foreman | 0.3 | 31 | 166.7395 | 1550.6773
| Gradall Lift | Days | 350 | 2 | 700 | [7 empty] | Carpenter | 2 | 28 | 166.7395 | 9337.4119
[5 empty] | 1360 | [13 empty] | BF/LF/SF | Total BF/LF/SF
10888.0893
Estimate Summary
[8 empty] | Total Project Hours |  | 166.7395
[8 empty] | Material $ |  | 12049.479
[8 empty] | Equipment $ |  | 1360
[8 empty] | Labor $ |  | 10888.0893
[8 empty] | Total Estimate |  | 24297.5683
Lumber Database | [20 empty] | Framing Crew | Time Alloc. | $/Hr
| Description | UOM | $/Unit | SF/BF/LF | [7 empty] | Description |  | UOM | $/Unit | SF/BF/LF |  |  |  |  | Foreman | 0.3 | 31
[21 empty] | Carpenter | 2 | 28
Pressure Treated | [11 empty] | OSB Panels
| 2x4x16 Pressure Treated | Pc | 5.789 | 10.6667 | [8 empty] | 4x8 x 3/8" OSB | Sheet | 5.22 | 32 |  |  |  |  | Production Rates
| 2x6x16 Pressure Treated | Pc | 8.351 | 16 | [8 empty] | 4x9 x 3/8" OSB | Sheet | 5.67 | 36 |  |  |  |  | Operation | Low Output | High Output | Prod UOM
[13 empty] | 4x10 x 3/8" OSB | Sheet | 6.08 | 40 |  |  |  |  | Tele Post | 1.5 | 2.5 | No./Hr
2x4 | 2x4x8 | Pc | 3.06 | 5.3333 | [8 empty] | 4x8 x 1/2" OSB | Sheet | 5.712 | 32 |  |  |  |  | 2x3 Plates | 50 | 54 | BF/Hr
| 2x4x10 | Pc | 3.66 | 6.6667 | [8 empty] | 4x9 x 1/2" OSB | Sheet | 6.2 | 36 |  |  |  |  | 2x4 Plates | 63 | 68 | BF/Hr
| 2x4x12 | Pc | 4.19 | 8 | [8 empty] | 4x10 x 1/2" OSB | Sheet | 6.68 | 40 |  |  |  |  | 2x6 Plates | 90 | 95 | BF/Hr
| 2x4x14 | Pc | 4.89 | 9.3333 | [8 empty] | 4x8 x 3/4" OSB T&G | Sheet | 9.982 | 32 |  |  |  |  | 2x3 Studs | 79 | 92 | BF/Hr
| 2x4x16 | Pc | 5.85 | 10.6667 | [16 empty] | 2x4 Studs | 100 | 115 | BF/Hr
| 2x4x18 | Pc | 6.58 | 12 | [7 empty] | LSL | 1-3/4" x 9-1/2" LSL | LF | 1.56 | 1.3854 |  |  |  |  | 2x6 Studs | 110 | 125 | BF/Hr
| 2x4x20 | Pc | 7.31 | 13.3333 | [8 empty] | 1-3/4" x 11-7/8" LSL | LF | 1.98 | 1.7318 |  |  |  |  | 2x8 Built up Beam | 150 | 260 | BF/Hr
2x6 | [12 empty] | 1-3/4" x 14" LSL | LF | 2.33 | 2.0417 |  |  |  |  | 2x10 Built up Beam | 200 | 310 | BF/Hr
| 2x6x8 | Pc | 4.24 | 8 | [8 empty] | 3-1/2" x 3-1/2" LSL | LF | 2.04 | 1.0208 |  |  |  |  | 9-1/2" Joists/Fim | 300 | 320 | LF/Hr
| 2x6x10 | Pc | 5.71 | 10 | [8 empty] | 3-1/2" x 5-1/2" LSL | LF | 2.56 | 1.6042 |  |  |  |  | 11-7/8" Joists/Rimi | 280 | 300 | LF/Hr
| 2x6x12 | Pc | 6.58 | 12 | [8 empty] | 3-1/2" x 7-1/4" LSL | LF | 3.01 | 2.1146 |  |  |  |  | 14" Joists/Rim | 268 | 288 | LF/Hr
| 2x6x14 | Pc | 7.67 | 14 | [8 empty] | 3-1/2" x 9-1/2" LSL | LF | 3.12 | 2.7708 |  |  |  |  | 16" Joists/Rim | 250 | 270 | LF/Hr
| 2x6x16 | Pc | 9.14 | 16 | [8 empty] | 3-1/2" x 11-7/8" LSL | LF | 4.98 | 3.4635 |  |  |  |  | 20+": Joists/Rim | 230 | 250 | LF/Hr
| 2x6x18 | Pc | 10.28 | 18 | [8 empty] | 3-1/2" x 14" LSL | LF | 7.14 | 4.0833 |  |  |  |  | 2x2 Blocking | 12 | 25 | BF/Hr
| 2x6x20 | Pc | 11.42 | 20 | [7 empty] | LVL | 1-1/2" x 3-1/2" LVL | LF | 1.91 | 0.4375 |  |  |  |  | 2x4 Blocking | 20 | 35 | BF/Hr
2x8 | [12 empty] | 1-1/2" x 5-1/2" LVL | LF | 2.044 | 0.6875 |  |  |  |  | 2x6 Blocking | 25 | 45 | BF/Hr
| 2x8x8 | Pc | 6.12 | 10.6667 | [8 empty] | 1-3/4" x 9-1/2" LVL | LF | 2.562 | 1.3854 |  |  |  |  | 2x8 Blocking | 30 | 50 | BF/Hr
| 2x8x10 | Pc | 7.64 | 13.3333 | [8 empty] | 1-3/4" x 11-7/8" LVL | LF | 2.933 | 1.7318 |  |  |  |  | Trusses 24'-40' Span | 2 | 3 | No./Hr
| 2x8x12 | Pc | 9.17 | 16 | [8 empty] | 1-3/4" x 14" LVL | LF | 4.221 | 2.0417 |  |  |  |  | 2x6 Rafters | 65 | 120 | BF/Hr
| 2x8x14 | Pc | 10.7 | 18.6667 | [8 empty] | 1-3/4" x 16" LVL | LF | 4.85 | 2.3333 |  |  |  |  | 2x4 Lookouts | 30 | 50 | BF/Hr
| 2x8x16 | Pc | 12.49 | 21.3333 | [8 empty] | 3-1/2" x 9-1/2" LVL | LF | 5.12 | 2.7708 |  |  |  |  | 2x4 Facia | 30 | 50 | BF/Hr
| 2x8x18 | Pc | 14.05 | 24 | [8 empty] | 3-1/2" x 11-7/8" LVL | LF | 6.02 | 3.4635 |  |  |  |  | 2x6 Facia | 35 | 60 | BF/Hr
| 2x8x20 | Pc | 15.61 | 26.6667 | [8 empty] | 3-1/2" x 14" LVL | LF | 7.22 | 4.0833 |  |  |  |  | T&G Floors | 150 | 160 | SF/Hr
2x10 | [12 empty] | 3-1/2" x 16" LVL | LF | 8.33 | 4.6667 |  |  |  |  | Wall Sheathing | 130 | 150 | SF/Hr
| 2x10x8 | Pc | 7.77 | 6.6667 | [7 empty] | GluLam | 5-1/8" x 9-1/2" GluLam | LF | 8.46 | 4.0573 |  |  |  |  | Roof Sheathing | 160 | 180 | SF/Hr
| 2x10x10 | Pc | 10.2 | 8.3333 | [8 empty] | 5-1/8" x 11-7/8" GluLam | LF | 8.897 | 5.0716 |  |  |  |  | Headers (Manufactured) | 180 | 240 | BF/Hr
| 2x10x12 | Pc | 11.9 | 10 | [8 empty] | 5-1/8" x 14" GluLam | LF | 9.69 | 5.9792 |  |  |  |  | Beams (Manufactured) | 230 | 280 | BF/Hr
| 2x10x14 | Pc | 13.89 | 11.6667 | [8 empty] | 5-1/8" x 16" GluLam | LF | 10.71 | 6.8333 |  |  |  |  | 1/2" Ply Soffit | 40 | 60 | SF/Hr
| 2x10x16 | Pc | 16.32 | 13.3333 | [7 empty] | Joists/Rim | [8 empty] | Aluminum Soffit | 40 | 60 | SF/Hr
| 2x10x18 | Pc | 18.6 | 15 | [7 empty] | I-Joist | 2" x 9-1/2" I-Joist | LF | 2.33 | 1
| 2x10x20 | Pc | 20.42 | 16.6667 | [8 empty] | 2" x 11-7/8" I-Joist | LF | 2.8 | 1
2x12 | [12 empty] | 2" x 14" I-Joist | LF | 3.89 | 1
| 2x12x8 | Pc | 10.58 | 16 | [8 empty] | 2" x 16" I-Joist | LF | 4.12 | 1
| 2x12x10 | Pc | 13.22 | 20 | [8 empty] | 2-1/2" x 9-1/2" I-Joist | LF | 2.44 | 1 |  |  |  |  | Rise | Run | Multiplier
| 2x12x12 | Pc | 16.15 | 24 | [8 empty] | 2-1/2" x 11-7/8" I-Joist | LF | 2.86 | 1 |  |  |  |  | 0 | 12 | 1
| 2x12x14 | Pc | 18.84 | 28 | [8 empty] | 2-1/2" x 14" I-Joist | LF | 3.74 | 1 |  |  |  |  | 1 | 12 | 1.0035
| 2x12x16 | Pc | 22.3 | 32 | [8 empty] | 2-1/2" x 16" I-Joist | LF | 4.16 | 1 |  |  |  |  | 2 | 12 | 1.0138
| 2x12x18 | Pc | 25.09 | 162 | [8 empty] | 3-1/2" x 9-1/2" I-Joist | LF | 2.68 | 1 |  |  |  |  | 3 | 12 | 1.0308
| 2x12x20 | Pc | 27.88 | 40 | [8 empty] | 3-1/2" x 11-7/8" I-Joist | LF | 2.961 | 1 |  |  |  |  | 4 | 12 | 1.0541
Studs (Fir S4S KD) | [12 empty] | 3-1/2" x 14" I-Joist | LF | 4.22 | 1 |  |  |  |  | 5 | 12 | 1.0833
| 2x4x92-5/8 | Pc | 2.43 | 5.3333 | [8 empty] | 3-1/2" x 16" I-Joist | LF | 4.65 | 1 |  |  |  |  | 6 | 12 | 1.118
| 2x4x104-5/8 | Pc | 2.9 | 6 | [7 empty] | Rim | [8 empty] | 7 | 12 | 1.1577
| 2x4x116-5/8 | Pc | 3.64 | 6.6667 | [8 empty] | 1-1/8" x 9-1/2" x 20' Rim | Pc | 24.35 | 20 |  |  |  |  | 8 | 12 | 1.2019
| 2x6x92-5/8 | Pc | 4.42 | 8 | [8 empty] | 1-1/8" x 11-7/8" x 20' Rim | Pc | 28.196 | 20 |  |  |  |  | 9 | 12 | 1.25
| 2x6x104-5/8 | Pc | 4.88 | 9 | [8 empty] | 1-1/8" x 14" x 20' Rim | Pc | 33.54 | 20 |  |  |  |  | 10 | 12 | 1.3017
| 2x6x116-5/8 | Pc | 5.61 | 10 | [8 empty] | 1-1/8" x 16" x 20' Rim | Pc | 37.01 | 20 |  |  |  |  | 11 | 12 | 1.3566
Posts (#2&Btr Green DF) | [11 empty] | Stair Material | [8 empty] | 12 | 12 | 1.4142
| 4x4x8 | Pc | 6.1056 | 10.6667 | [8 empty] | 1-1/4" x 11-7/8" OSL Stringer | Pc | 47.341
| 4x4x10 | Pc | 6.8356 | 13.3333 | [8 empty] | 12" x 12' Super Step Stair Tread | Pc | 12.985
| 4x4x12 | Pc | 7.5656 | 16 | [8 empty] | 1" x 8" #2 KD Pine Riser | Pc | 6.944
| 4x4x14 | Pc | 8.2956 | 18.6667 | [7 empty] | Deck Material
| 4x4x16 | Pc | 9.0256 | 21.3333 | [8 empty] | Trex 5/4x6x12 | Pc | 20.986 | [5 empty] | Spacing | Multiplier
| 4x4x18 | Pc | 9.7556 | 24 | [8 empty] | Trex 5/4x6x16 | Pc | 27.979 | [5 empty] | 12" OC | 1.25
| 4x6x8 | Pc | 19.04 | 16 | [8 empty] | Trex 5/4x6x20 | Pc | 34.979 | [5 empty] | 16" OC | 1
| 4x6x10 | Pc | 20.5 | 20 | [8 empty] | Trex Rim 1x12x12 | Pc | 48.783 | [5 empty] | 19.2" OC | 0.9
| 4x6x12 | Pc | 21.96 | 24 | [7 empty] | Hardware/Misc. | [8 empty] | 24" OC | 0.75
| 4x6x14 | Pc | 23.42 | 28 | [8 empty] | 5/8x3" Sq Washer | Ea | 0.861
| 4x6x16 | Pc | 24.88 | 32 | [8 empty] | 5/8 Hex Nut | Ea | 0.21
| 4x6x18 | Pc | 26.34 | 36 | [8 empty] | 5/8 Flat Washer | Ea | 0.21 | [5 empty] | Stick length |  | Waste
| 6x6x8 | Pc | 23.42 | 24 | [8 empty] | 3-1/2"x50' Foam Sill Seal | Roll | 2.737 | [5 empty] | 8 |  | 1
| 6x6x10 | Pc | 24.88 | 20 | [8 empty] | 5-1/2"x50' Foam Sill Seal | Roll | 3.409 | [5 empty] | 10 |  | 1.05
| 6x6x12 | Pc | 26.34 | 36 | [8 empty] | MD400 29 oz Constr. Adhesive | Tube | 1.953 | [5 empty] | 12 |  | 1.1
| 6x6x14 | Pc | 27.8 | 42 | [8 empty] | H1 |  | 0.56 | [5 empty] | 14 |  | 1.15
| 6x6x16 | Pc | 29.26 | 48 | [8 empty] | H2-5 |  | 0 | [5 empty] | 16 |  | 1.2
| 6x6x18 | Pc | 30.72 | 54 | [16 empty] | 18 |  | 1.25
20
24
On your own...
On your own...

## Sheet1
Description | UOM | $/Unit | Qty | Total
4000 psi Concrete | CY | 138 | 63 | 8694
Plywood 3/4" | Sheet | 35.47 | 42 | 1489.74
2x10x16 | Ea | 27.16 | 46 | 1249.36
11433.1